|  | CONFERENCE GUIDELINES New Zealand Farm Forestry Assn (Inc.) P O Box 1122 Tel 04 472 0432 Wellington 6015 Fax 04 473 6904 Email nzffa@clear.net.nz |
| --- | --- |

[Revised March 2010]

# BACKGROUND

The Annual Conference is held alternately in each island.  The responsibility of the National Association to stage a conference is delegated to the chosen branch.  The designated branch usually forms a Conference Committee to organize the Conference.  The National Association remains ultimately responsible for the Conference and the Conference Committee or hosting branch reports to it.

A branch considering holding a conference should apply to Council at least three years in advance.  Considerations include:

- Sufficient accommodation for conference participants. (Set a realistic upper limit on attendance.)

- A venue large enough for those attending (especially Opening and Awards Dinners and AGM).

- Anterooms for the National Executive meeting usually the day before the Conference, and the Council, Branch Management, Past Presidents and Neil Barr Foundation Trustees meetings usually held on the first day of the conference.  Meeting audio-visual equipment requirements are detailed elsewhere.

- A core of 5-8 keen people to organise the conference.

- A support group of up to 20 people to assist with mundane tasks during the conference (driving, directing buses, etc).

- Adequate transport, public address systems and catering.

The National Association provides a float, usually of $1,000 (but organising committees who use professional conference organizers like EventMergers often require $3,000), use of the Association’s conference GST number (76-367-043), and the assurance that any loss will be covered.  On the other hand, if there is a net profit it is distributed as follows:

- the branch hosting the conference is entitled to 30% of the net audited profit of the conference – the rest goes to the NZFFA National Office

- usually the entire audited profit plus the float of $1000 is sent back to the Association with a full set of audited conference accounts – the 30% share is then send back to the host branch

- note that the chainsaw donated by Husqvarna for auction is part of the sponsorship deal National Office and the return from this should be remitted to National Office and is not part of the conference profit.  All other auction proceeds belong to the conference

The organising Branch will decide how they wish to spend their share of Conference profits.  Some projects to date include:

- Establishment of demonstration trial areas

- Establishment of charitable trusts

- Supply of books to local schools and libraries

- Supply of equipment for branch field days (speaker systems)

- Support a local arboretum

PLANNING A CONFERENCE

At least two years before the conference, gather together a group of 5-8 enthusiastic individuals to be the Conference Committee.

Develop the conference theme, considering the following:

- A written theme is optional - most conferences have a theme and prepare a brochure for distribution at previous conferences as well as letterhead

- Most farm foresters like to consider it a working conference with a balance of informative field days/meetings and social events

- At the 1999 AGM there was a call for more workshops and fewer field trips.  At the Hastings Conference in 2001 there was a call for more field trips and fewer meetings.  Best formula is base your conference’s format on recent conferences, but modify it in the directions for which attenders seem to be indicating a preference.

- Possibly hold an evening public meeting with an interesting speaker and plenty of time for discussion

- Set the date, preferably early/mid April.  March can squeeze National Executive requirements.  Avoid Easter.

- Plan field days to showcase what your district has to offer.

- Provide variety and ample discussion time.

- Plan a wet weather back-up.

- Use speakers who have knowledge of local farming, forestry, geology or history.

- Use a different speaker for each subject. 20-30 min including questions is ideal.

- Use local organisations for transport, display material, sponsorship and speakers.

- No public meeting on the free night.

- Contact the Indigenous Forest Section and other interest/action groups to determine their requirements at conference.

- There is no absolutely correct way of running a conference.  Each one is its own unique experience.

Liaise with the National Executive, who will require a draft programme and budget by the July Executive Meeting prior to the conference.

Organise local awards

(see end)

##### CONFERENCE COMMITTEE AND FUNCTIONS

These responsibilities may be combined depending on the strengths and interests of your committee.

1.	Chairperson/Convenor

- Arrange speakers and prepare notes of introduction

- Arrange people to thank speakers

- Arrange facilitators for workshops, if required

- Prepare programme to present to National Executive

- Be strong on organisation and delegation

- Support and supervise committee members

- Control proceedings during conference

- Is responsible for overseeing each day’s events

- Liaise with National Executive

2.	Secretary

- Write letters and maintain correspondence file - access to a word processor and fax required

- Record committee decisions

- Advise National Office of the number of registrants so that sufficient Annual Report documents can be printed.

- Arrange for at least one committee person accompanying each field trip part to have a cellphone to take urgent calls.

- Make information requests to National Office

3.	Conference Registrar

- Will require a computer, email, postal address, fax machine and answerphone – more than one phone line desirable

- Prepare registration form for November and February issue of the NZ Tree Grower (previous forms are a good guide).  Check the deadline date for delivery of the forms to the NZ Tree Grower.  The publisher can arrange printing of the forms but a local printer is usually more cost effective.

- Make sure the programme is on the form and includes the timing of the Branch Management and Council meetings.  Indicate that day registration is an option.  If people write their options, rather than fill out a table of options, this saves space.

- Keep forms clear and simple to follow - trial on a volunteer to check clarity and programme.  Prices to be GST inclusive

- Include registration for Indigenous Forest Section/Cypress Action Group/AMIGO, especially if they are holding field trips

- Consider sending registration forms to non-NZFFA members who attended the last conference

- Liaise with National Office regarding placing registration form and other conference material on the NZFFA website.

- All records must be computer-based for ease of sorting and checking.  Regular back-ups and up-to-date virus protection are essential.  National Office has the Excel files that were set up for the Hastings Conference in 2000 and have been used for several later conferences.

- Prepare a master list of registrations for name tag printing.  Sometimes different coloured tags are used for Conference Committee, National Executive, Patron and First Timers.

- Organise/control registration desk

- Ensure limited office facilities are available during conference. It is especially useful to have someone who can assist people who turn up late after buses have gone

- Liaise with catering officer to ensure meals for day attendees

- Be aware that if the Registrar is the only contact given in conference advertising, he/she will get all the calls.  Better idea is to bracket the Registrar as contact with another person who can handle non-registration matters (e.g. Conference Convenor or Organiser, or even just another committee member who has good access to communication media and desirably is available during the day).

4.	Conference Treasurer

- Requires attention to detail

- A systems person who can cope with requests for changes and special treatment

- Maintain a list of registered participants, payments and special requirements

- A spreadsheet is a useful way to record information

- Open conference bank account

- If required, request a float from National Office one year before conference - $1,000 is usual but the amount is negotiable

- Bank all monies even if wrong amount

- Ensure monies are accounted for

- Keep balance sheet up to date

- Prepare budget to allow at least a $3,000 profit but note that the National Office costs usually exceed $5,000 and so a $10,000 surplus is required to ensure a profit is made after 30% is returned to the host branch.

- All budgeted items to be budgeted on GST exclusive basis

- Budget for extra or alternative functions (e.g. day registrations)

- Use NZFFA special conference GST Number (76-367-043).  The GST returns will be sent to you from National Office to fill in – payments basis, 6-monthly periods Jan-June and July-Dec.

- If registrations are not being handled by a professional organiser, you can use the National Office credit card clearing facility - contact the administration officer for advice on this.  If using National Office, the registration form must have the statement: Sorry, American Express not accepted.

- Determine cancellation policy, e.g. $20 charge for early cancellation and $50 for within a fortnight or month of conference

- Prepare budget by previous July for presentation to National Executive

- Liaise with registrar re money still owed

- Complete final budget – request examples from previous conference committees or national office

- Assist other branches with their planning as requested

- After the conference close bank account and send monies to National Office (refer to percentages on page 1 of these guidelines)

- Format for conference surplus funds to National Office

- Send surplus funds back as a single payment after all the accounts have been finalized, or else if finalising the accounts is delayed, transfer instalments to National Office

- Finalise accounts and provide a profit and loss statement

- Arrange for the accounts to be audited

- Return balance of funds and close account

- If conference committees are unsure about any aspect regarding the conference profit they need to contact the National Executive

- The spare (3rd) chainsaw donated by Husqvarna is auctioned at the conference and the proceeds go to the Association to offset the costs of judging the Husqvarna NZ Farm Forester of the Year competition.  Otherwise the receipts from the auction are treated like all the other conference receipts.

5.	Accommodation Officer

- Block book as soon as possible before the conference. This should attract discount tariff and free services such as meeting rooms and equipment

- It makes transport easier if accommodation is on one transport route

- National Executive normally arrive a day early and all stay at the same venue

- Arrange to meet all delegates who arrive by public transport

- Work closely with registrar - liaise on almost daily basis by last few weeks

- Co-ordinate incoming and departing transport arrangements (this may be in conjunction with a travel agent)

- It is useful to delegate someone to organise decorations

- Consider organising creche facilities - if so, have Registrar put question re use in registration form

- In the past, conference committees often made all the accommodation arrangements, and if so the accommodation officer would do this and the following two points apply*

- *Obtain guaranteed rates in writing before advertising in the NZ Tree Grower

- *Band accommodation into price ranges for registration form in November and February issue of the Tree Grower.  Full range of prices needed.  Majority of delegates request cheaper accommodation

- Latterly conferences have offered some assistance to the delegates to find accommodation, such as listing and pre-booking those on the bus routes, but the actual arrangements are left to the delegates themselves.

6.	Transport Officer

- Obtain quotes for full size coaches, smaller buses and minibuses

- Oversee field day transport arrangements

- Arrange local transfer of delegates to accommodation

- Arrange local transfer of delegates to conference venues and meetings, and back to accommodation - if appropriate arrange bus stop signs at pick-up points

- Arrange local departing transport

- Provide each bus driver with maps and clear instructions, and practise with dry runs to get timing guides

- All buses require a working PA system with good mikes that are easy to use

- Ensure a spare bus is available to cover for mechanical break-downs

- Travel field trip routes in advance with senior driver or manager, take at least one bus and ute on dry run

- Plan routes to allow sufficient parking, plus turning room when other buses are parked

- Check that farm roads/tracks can cope with up to 8-10 buses whatever the weather

- Check routes just before conference (overgrowth/scratch the paintwork/weather damage/road works, etc, cut branches back etc.)

- Allow at least 20 minutes to load buses at field stops (but when conditions are good it can take less and so field day organizers should have a Plan B to absorb a few extra minutes from time to time)

- Organise head courier; lead all briefing/debriefing sessions with couriers

- Obtain a low slung 4WD to transport aged, disabled and pregnant people

- Load juice, apples and snacks daily on each bus

- Arrange for Red Cross or St. John’s to provide first aid, in return for a donation. (Also possibly an ambulance? - was used at Taranaki)

- Arrange for 2 people to have transport on hand and act as gofers during the conference

- Install identifying numbers and/or destination labels front and back of each bus

- During the conference, check that any repairs needed are carried out, and that buses carry spare tyres

- Middle Districts Branch found that in some cases it would have been better to have 2 small buses in preference to a larger bus for pick-ups. This was the time factor, not the bus capacity.

7.	Head Courier

- Allocate one courier per bus to give a commentary describing the area being driven through. Couriers should know the area themselves, and not just read someone else’s notes. Commentaries to be interesting but brief - people on the buses like to chat to each other

- Couriers to be responsible for food on bus trips and rubbish bags

- Make sure there are back-up couriers in case any drop out for whatever reason

- Make sure each bus courier has a cellphone

- With transport officer, brief the couriers before each day’s excursions - allow up to 30 minutes. Debrief each evening

- Useful to have couriers confirm to passengers at end of each day what the next day’s programme is, and when/where it starts. If next day’s programme extends into evening without returning to base it is especially desirable to confirm this the day before

8.	Field Day Officer

- Invite speakers; obtain copies of speeches for proceedings.  All speeches/talks to be peer reviewed beforehand by competent people

- Time the field trips.  Allow a minimum of one hour in and out to look at anything or get on and off bus.  Not too many stops - but try to plan venues so that people aren’t sitting on a bus for more than about an hour at a time

- Arrange port-a-loos - allow one port-a-loo per 50 people

- Make sure shade/shelter available

- Arrange practical details such as signs, taking down fences, ensuring gates are/can be unlocked

- Arrange robust sound system, with good batteries, fitted to 4WD vehicle/farm bike and roving hand-held mikes, for all groups. Make sure people know what plugs in where.

- Organise back-up sound system

- Make sure speakers know how to use the mikes and face the group

- Educate speakers to repeat the question

- Coordinate with couriers on buses with interesting range of info and local knowledge

- Check out the position as regards public liability, OSH requirements, etc.  The Association’s public liability insurance covers the conference field days.

- Arrange hi-viz jackets for committee members (and helpers) on field trips

- Arrange supply of cardboard/felt pens

- Appoint a time-keeper for each venue and someone (especially younger people/women) to give vote of thanks

- Useful if basic washing facilities can be organised after long visits

- Note that people become weary after a long day, especially if they do not get a break back at their accommodation before the evening meal.

9.	Catering Officer

- Organise all meals from beginning to end of conference, including lunches, AM and PM teas

- Conference costs generally include all meals except breakfast and one evening meal

- To handle 300 people quickly, have at least 5 dispensing points

- If serving tables, at least 10 waiters will be required

- Have one helper exclusively responsible for the alcohol area/ supervising the bar

- Set a top table for President and distinguished guests on Opening night and Awards night

- Arrange place names for distinguished guests

- Make sure tables aren’t too big for people to talk across (rectangular better than round)

- Ensure new people are mixed in with old hands

- Arrange a meal with the National Executive and Conference Committees and their spouses on the night before the conference (Association expense)

- Executive arrive on the day before conference and usually require a light lunch for executive and spouses plus afternoon tea. (Association expense)

- Arrange morning tea for the conference debrief on the day after the conference.

- A packed lunch is adequate for field trips: e.g. a bread roll, 2 sandwiches, a muffin, a cake and a piece of fruit (or equivalent).  Arrange sufficient hot water and plastic or disposable cups fast serving of tea/coffee.  Supply fruit juice and drinking water

- Arrange morning and afternoon tea (fruit/drink/energy snacks) to accompany each bus – can be cost effective to purchase supermarket specials or from a grocery warehouse – people do not take one of everything every time, and so overall numbers work out at less than the total delegates multiplied by total morning and afternoon teas.

- Remember to include bus drivers and field day helpers in the numbers for catering

- Allow 5 extra dinners and 20 extra lunches per 300 people.  Liaise with registration desk to make sure these amounts will cater for day attendees

- In the past local organisations have been used to supply lunches, but food handling regulations now make professional caterers desirable

- Cater for vegetarians, i.e. people who eat eggs and dairy products but not meat or fish

- Obtain all quotes in writing

10.	Sponsorship Officer/Trade Display

- Contact possible sponsors up to 12 months ahead – earlier is better

- Possibilities:

Satchels	Name tags	  Stationery/pens		Brochures

Trees		Happy Hours	  AM/PM tea			Field trips

Product		Cash!!		  Sponsorship of whole day

- Obtain list of NZFFA major sponsors from National Executive  - at the moment Husqvarna (who sponsor the Farm forester of the Year Awards) are the main one

- Liaise with National Office regarding Husqvarna Farm Forester of the Year Awards - vacuum cleaners, chainsaws and safety gear.  Ensure you know who is dealing with the Husqvarna representative and what the his requirements are.  Husqvarna may want to involve their local agent.

- Prepare sponsorship proposal and distribute.  Each conference should approach both local and national sponsors, including those used at recent previous conferences.  It is important that the propositions offered to sponsors address the value sponsors will get in return for their support.

- Negotiate special deals and get advertising copy for proceedings (again coordinate with the Tree Grower advertising)

- Follow up with a personal visit/phone call/letter to sponsor by local representative

- It can save time, money and anguish to employ a professional sponsorship organiser - even if only for long enough to get things under way.  But the professional must understand your purpose/aims/culture

- Draw up a sponsorship contract form setting out agreed obligations - this can provide comeback if the money isn’t paid

- Arrange opportunities for sponsors to say a few words if possible

- Consider a sponsorship appreciation certificate

- Arrange trade display area for sponsors and others who wish to make a display

- Allocate space for trade displays - preferably an area that is lockable or has another form of security

- Maintain contact with those who have booked a display area – there are often changes

- Be prepared for those who turn-up without a booking

- Be there when they set up (to ensure they stay in their allocated space) and pack up, be prepared to help (trolleys, etc)

11.	Publicity Officer

- Involve the local media, radio and trade magazines at least 6 months before the conference

- Invite them to field days and keep them informed

- Liaise with NZ Tree Grower associate editor, Harriet Palmer, about publicity for the Conference

- Complimentary registrations may be provided for media people, but ensure it is a value for value situation (talk over with a National Executive person if in doubt)

- Prepare a short promotional article for the August, November and February issues of Tree Grower.  Ensure the programme is in the promotional material

- Organise a conference article for the May NZ Tree Grower

- Arrange media coverage before, during and after conference

- Liaise with local and national media

- Arrange a photographer to cover the opening night speeches and awards.  Photographer on the opening night to take high quality colour photographs of:

- Minister of Forests (if present)

- Transpower Landcare Trust Award for Innovation in Sustainable Farm Forestry

- Husqvarna North and South Island Farm Forester of the Year Award Winners

- Others, i.e. President

Proofs to be available next day for:

- Press statements on the above

- Branches to use immediately, i.e. distribute to local newspapers and not have to wait for photos to arrive two weeks later.

With modern digital photography, photos taken during the conference can be displayed on a screen during formal dinners, etc.

12.	Proceedings Editor

- Once speakers have been confirmed, request papers for the Proceedings. Give deadlines and contact details

- Biographical notes are helpful and could be asked for at the same time

- To the extent possible, get information transferred electronically on disk or via e-mail, plus hard copy in good black and white resolution for any graphs, tables, diagrams and photos.  Fancy graphics with coloured shading do not reproduce well

- Give guidance on 
* space limitations
* the word processing/DTP program and versions being used
* margins, font, styles, etc that you plan to use, eg fully justified text, 11 point Times 
   New Roman, headings bold, caps, sub-headings bold initial caps, etc.
   Some copy will still arrive handwritten or via fax, and have to be keyed in, but it 
   saves much time and effort to keep this to a minimum

- When setting deadlines always allow yourself additional time - and never let anyone else know what your real final deadline is (or they will work to that and destroy your emergency comfort zone)

- Maintenance of up-to-date virus protection is essential

- Print out all copy as received, file in the order of the programme

- Liaise with sponsorship officer for advertisements to be included.  Request copy well before printing deadline if the printer is to set them.  Bromides of advertisements are best, but crisp black and white copy is OK.

- Maintain close contact with the printer.  Get an understanding of the technical process and limitations.  Confirm they have scheduled the dates for your job and are ready to run with it when it comes in

- Delegates list (first names, surnames, town of residence) should be printed last to get all names, but note privacy issue – have box on registration form for delegates to tick if they want their names in the proceedings

- Note that National Office requires 10 copies of the Proceedings for legal deposit at the National Library and supply to libraries.  It is a good idea to offer copies to your local libraries.

13.	Decorations and entertainment

- Organise decorations for displays, tables and conference rooms

- Keep entertainment simple and short, allow plenty of time for people to talk

- Music in the background (not loud) helps to create atmosphere

#### PRE-CONFERENCE DETAIL

## A.	General

- Organise someone to be gofer for National President throughout the conference

- Involve national press

- Keep one evening free

- Provide for all age groups and interests

- Allow time to renew old acquaintances and to relax

- The last night is a good time for an informal function

- Have a contingency plan in case of bad weather or speakers who can’t turn up

- Make time for thanking local committee

- Liaise with National President’s regarding opening speaker – if you decide to invite a cabinet Minister the President usually extends the invitation

- Presentation of Husqvarna Farm Forester of the Year and other Awards can be on different nights, but in recent years we have tended to have them all on an Awards Evening which then has a tendency to run over time.  A condition of the Transpower Landcare Trust Innovation Award is usually that it is presented during the Awards Dinner which includes the Farm Forester of the Year presentations.

- If you have a guest speaker, no longer than 30 mins and in between courses

- Have only a professional and entertaining after-dinner speaker - not necessarily on forestry subject

- Any entertainment to be simple and short.  Background music not to be obtrusive

- Consider liaising with/involving other environmental organisations

- Remember to select local awardees for the Neil Barr Agroforestry and Peter Smail Shelter Awards which can be presented at a field trip.  The book tokens presented to mark these awards are arrange by National Office

- Free night is mandatory

- Be aware the some people will want to leave early on the last day.

- If there is an evening speaker, delegates should be given time to change clothes after field day

- All reports to the AGM are printed by National Office in the Annual Report document which should be available at registration – in recent years it has become customary to not place the Annual Report document in the conference satchels as not everyone wants one

- Matters passed at Council meeting (or Business Session of the AGM) should be approved at AGM with discussion only

- I has become customary in recent years for a “Business Session of the AGM” to be held separately from the Formal Session of the AGM.  This enables more free-ranging debate at the Business Session and more emphasis on the Executive providing information to members on the issues of the day facing the forestry industry and NZFFA.

- The deadline for remits is 1 November preceding Conference, and National Office usually informs branches of upcoming remits in January so that they can be discussed at branch annual meetings in February.

- If conference committees are unsure about any aspect regarding the conference profit they need to contact the National Executive.

B.	Opening and Awards Dinners

- Chairperson or Conference Convenor to liaise with National President over programme

- Arrange photographer and media (radio and newspaper) coverage of speeches and awards

- Have at least 5 serving points or 10 waiters to cater for 300 people

- During the evening inform delegates of procedures and details of the following day’s programme – remember some may leave early

- Conclude the formal part of the evening by 9.30 p.m.

- It has become customary to hold a separate Awards Dinner.  Presentation of Awards occupies most of the available time.  Awards include: Husqvarna Farm Forester of the Year for both North and South Islands, Transpower Landcare Trust Grants Award for Innovation in Sustainable Farm Forestry, possibly a Neil Barr Foundation Award, possibly the Neil Barr Award (agroforestry) and Peter Smail Award (shelter).  The latter two are chosen by the host branch and are often younger farm foresters, although there is no actual age criteria.

- The Auction is usually held at the end of the Awards Dinner as a convivial occasion to wind up the evening – important to have an auctioneer who enters the spirit of the occasion, only a small number of items to auction, and not to let it get too late.

C.	Satchels & Registration

- Pack these in the week before the conference - include Proceedings, a list of delegates (may be in the Proceedings), a map of the town and the district, and a card programme

- The Annual Report document now has the accounts, President’s Report, Treaurer’s Report, all other reports, remits, agendas and minutes of previous AGM.  Liaise with National Office on the number that need to be printed – note in recent years the Annual Report documents have been available at registration but have not been placed in the conference satchels as not everyone wants them.

- Coloured stickers or tickets may be included with the name tag as entry to specific functions. Identify first-time Conference goers.

- The Executive and Patron require ribbons or different colour name tags

- You may choose to have satchels waiting for delegates when they arrive at their accommodation so that they do not need to report to registration so soon, but this has to weighed up against the extra work and confusion it may create.

- Ensure all accommodation has a copy of the programme at the front desk

- When registering delegates, allow plenty of space and multiple desks (perhaps alphabetical)

- Have a desk for general enquiries and pamphlet displays throughout the conference

D.	Meeting Requirements

- Executive

- Day before official opening starting 1:00 p.m. - arrange meeting room and afternoon tea, liaise with National Executive whether lunch also required.

- Requirements:  Seating for 8-10 in boardroom setting, overhead projector, whiteboard with pens and eraser, photocopier or access to one nearby.

- The meeting sometimes resumes early on the morning of the Council meeting and official opening

- Morning after conference 8.30 - 10.00 a.m.

2	Research Committee

May meet one evening or at the same time as another meeting.  Requirements similar to Executive but boardroom setting not essential and numbers may be greater.

3	Branch Management, Business session of the AGM and Council Meetings

Please print the times in the Tree Grower registration form as well as in your programme (times are subject to consultation with preceding conference committees and the National Executive).  To help give an indication of numbers, have boxes to tick on the registration form if registrants expect to be at these meetings.  An indicative timetable follows:

9.30 a.m.		Morning tea for 50

10.00 a.m. - 12 noon	Branch Management - (50)

Lunch	(Allow for the number expected for the Business Session)

1.00 – 3.00 p.m.	Business Session of AGM (80)

3.00 p.m.	Afternoon tea for 80

3.30 - 5.00 p.m.	Council Meeting for Branch Councillors (40)

Requirements:	Overhead projector and screen set up and working before, whiteboard, pens and eraser, extension cord, table at door for people to pick up papers, seating at front table for four, speaker system, roving microphones.  If required, Power Point projector with laptop and screen.

4	Past Presidents

Usually takes places place at the same time as the Council meeting – expect 10 to 15 – may not be held if there is no business to transact.

5	 Neil Barr Farm Forestry Foundation Trustees

Usually takes places place at the same time as the Council meeting – expect 5 to 6

6	AGM

Requirements:

- Public address system, lectern and standing microphone plus roving microphones

- Record the proceedings

- Overhead projector and screen

- If required, Power Point projector, laptop and screen

- PA system, computer and overhead not on same circuit/plug, to reduce interference/static

- All working before the meeting starts

- Whiteboard, pens and eraser

- Person available to put overheads on and off as this saves time

- Top table for 10 on a raised platform

- Water and glasses on table

- No other meetings organised at the same time as or before the end of the AGM.  Items of general business in writing to the Executive Officer with name and branch before meeting starts

6	Indigenous/Cypress/AMIGO/Eucalypt/Sequoia

Contact them for their requirements - these meetings should not coincide AGM with the conference organizers must make provision for these meetings at other suitable times and note that some delegates desire to attend more then one.

### POST-CONFERENCE

Be available immediately after conference for a debriefing with National Executive and the next year’s conference committee representatives.  Debriefing is usually held at 10.00 a.m. (after the Executive meeting) on the day after conference

Send out thank your letters and prepare final accounts.  Report to National Executive and make notes for next host branch.  Send a copy of these notes to National Office to help update these Conference Guidelines.

New Zealand FARM FORESTRY ASSOCIATION

CONFERENCE PLANNING CALENDAR

(for an April Conference)

###### APRIL

- Conference Convenor and/or other responsible organising committee representatives should attend the previous conference debrief

MAY

- Complete field days plan

- Organise arrangements at conference venue

- Begin contacting sponsors and don’t stop until the conference starts

- Book accommodation

- Immediately after one conference is over the NZFFA website is available to publicise the next

JUNE

- Get first quotes from bus companies

- Get catering quotes

- Finalise theme

- Contact field day speakers and give them subjects. Ask for written notes for Conference booklet

JULY

- Ask for written quotes

- Draw up programme and budget and present to National Executive Committee

AUGUST

- Order satchels or backpacks or arrange for sponsor to order them

- Start assembling reports for the Tree Grower

- Start assembling field day and bus notes

SEPTEMBER

- Draft conference registration form

- Supply article and photos for November NZ Tree Grower

OCTOBER

- Ensure registration forms are dispatched by the deadline for the November NZ Tree Grower

NOVEMBER

- Select bus couriers

- Select back-up crew for all conference jobs

- Check all catering facilities

- Publicise the conference at every opportunity

DECEMBER

- Put together notes for satchels/backpacks

- Start to organise gifts for delegates

- Registration begins

- Have a good rest over Christmas

- Supply article and photos for February NZ Tree Grower

JANUARY

- Arrange apples and drinks for buses

- Keep an eye on registration numbers

- Size of conference should start to become apparent and most details finalised

FEBRUARY

- Start day registrations

- Advertise locally (Rural Delivery)

- Check all conference arrangements

- Satchel notes away to printer

MARCH

- Check all times and arrangements of field days, fine tune if necessary

- Get notes back from printer

- Assemble all conference materials

- Final fine tune

- Print registration lists

APRIL

- Put materials into satchels

- Make up gifts for delegates

- Distribute satchels and gifts to accommodation if the committee has decided to do this.

- Final briefing for all involved

### LOCAL AWARDS

The Neil Barr Award for Agroforestry and the Peter Smail Award for Shelter are judged by the branch and awarded to members of the branch organising the conference.  Branches should draw up a short list, aiming to nominate three young members.  National Office supplies $150 Touchwood book vouchers as prizes.

The ceremony can take place out in the field.  Either way, the timing of the presentation should be formally placed on the conference programme.  Peter Smail presents the Peter Smail Award for Shelter if he is present – otherwise liaise with the National President over who the presenters should be.

Neil Barr Agroforestry Award

Neil, a farmer and then a farm forester, was always keen to promote the use of trees on farms. He was a committed disciple of Dr WRJ (Wink) Sutton and believed the most important undertaking in a woodlot or forest was to thin.  The standing trees then had to be pruned.

This resulted in wide-spaced trees that produced short fat pruned butt logs that accounted for some 80 percent of the value of the crop at harvest.  It also meant that grass was available under the trees for a considerable part of the rotation.  The trees also provided considerable shelter to animals in adverse weather.  Latterly the principles of agroforestry have been modified by the need to grow trees (especially radiata) closer together to achieve quality timber.  Neil was also a great exponent of alternative species.

The purpose of this award is to encourage and reward a young farmer who has learnt from what Neil espoused and put into practice what she or he has learnt.  The award will generally be made annually, and given to a young farmer who is a member of the branch hosting the National Conference.  The hosting branch will determine the recipient.

The recipient will receive a book voucher to the value of  $150.00.  The award will be funded by the National Association.

Peter Smail Shelter Award

Peter farmed for many years on the then windswept Canterbury plains. He recognised the need for shelter for the wellbeing of livestock, crops and human beings.  His work in the design and placing of shelter has become legendary both in New Zealand and overseas.

The purpose of this award is to reward a young farmer who has learnt from what Peter has espoused, and put into practice what he or she has learnt.  It is intended that the award be made annually, subject to suitable nomination, to a member of the branch hosting the national conference. This will not only provide publicity for the recipient, but also can provide additional publicity for the host branch.  The host branch will determine the recipient.

The recipient will receive book vouchers to the value of $150.00.  The award will be funded by the National Association.